## Summary
APP_05 — Risk & Opportunity Summary
As at 24 April 2026 · Rev 3 · 21 risks · 9 opportunities
Risks by exposure band (residual)
Low (3-7) | 15
Medium (8-13) | 6
High (14-19) | 0
Very High (20-24) | 0
Risks by status
Active | 13
NEW | 8
Closed | 0
New risks added in Rev 3
R-06 | Benzene exposure (from COSHH_23)
R-10 | Water (Special Measures) Act 2025 pass-through
R-11 | Employment Rights Act 2025
R-12 | Worker Protection Act 2023 duty-to-prevent
R-13 | ISO standards transitions 14001/9001/45001
R-14 | NUAR migration (DUAA 2025)
R-18 | PFAS UK REACH restrictions (monitoring)
R-21 | Water-sector skills shortage

## Risks
A M Water Services — Risk Register
APP_05 Rev 3 · As at 24 April 2026 · 21 risks · Inherent A+B+(C*D), Residual A'+B'+(C'*D')
# | Ref | Category | Risk description | A | B | C | D | Inherent score | Existing controls | Treatment | A' | B' | C' | D' | Residual score | Owner | Target review | Status | Notes
1 | R-01 | Resource / People | Loss of key staff with required competencies (WIRS, EUSR, NRSWA). Loss of staff to accident / incident. | 3 | 2 | 3 | 2 | 11 | #TEAM culture, performance reviews, succession planning, H&S training, competency tracking | Mitigate | 2 | 2 | 2 | 1 | 6 | Aaron Mason | 2027-06-01 | Active
2 | R-02 | IT / Cyber | Cyber-attack / ransomware (water sector is critical-infrastructure target — cf. South Staffs Water 2022, Southern Water 2024). Data loss, compliance data, WIRS records. | 4 | 3 | 2 | 2 | 11 | External IT support, firewall, anti-virus, cloud backup, BCP | Mitigate + Transfer | 3 | 3 | 1 | 1 | 7 | Leanne Mason | 2026-10-01 | Active | Review alignment to forthcoming UK Cyber Security & Resilience Bill
3 | R-03 | Premises | Loss of Northampton office & equipment. Relocation costs. Equipment / tools / records loss. | 3 | 1 | 2 | 1 | 6 | BCP, maintenance, fire-risk assessment, insurance, remote working | Accept + Transfer | 2 | 1 | 1 | 1 | 4 | Aaron Mason | 2027-06-01 | Active
4 | R-04 | H&S — excavation & site | Fatalities / injuries in water-infrastructure work: excavation collapse, confined-space, live-mains, manual handling, highway working. | 4 | 4 | 2 | 3 | 14 | RAMS programme, trained staff, equipment checks, inspections, emergency procedures, field RAs (RA01-25), MSs (Section 2 + 3) | Mitigate | 2 | 4 | 1 | 2 | 8 | Jason May | 2027-06-01 | Active
5 | R-05 | Occupational health | Occupational-health claims: manual handling, HAVS, noise, waterborne disease, stress / MH. | 3 | 3 | 3 | 2 | 12 | Health surveillance programme, training, low-vibration tools, PPE, wellbeing support | Mitigate | 2 | 3 | 2 | 1 | 7 | Sean Ashton | 2027-06-01 | Active
6 | R-06 | Occupational health — benzene | Carcinogen (benzene <1% in BP unleaded petrol — COSHH_23) exposure for operatives routinely refuelling petrol tools. HSE EH70 statutory surveillance obligation. | 4 | 4 | 2 | 2 | 12 | Open-air refuelling, cold-tool rule, nitrile gloves, 20 L quantity limit, SOP 8.7 health surveillance to activate 6-monthly | Mitigate | 3 | 4 | 1 | 1 | 8 | Sean Ashton | 2026-09-01 | NEW | Review surveillance arrangements before 1 Aug ordering cycle
7 | R-07 | Supply chain | Loss of key subcontractor / supplier. WIRS-compliance gaps in supply chain. Quality issues. Price rises. | 2 | 2 | 3 | 2 | 10 | Approved supplier list (APP_19), 32 SARs (currently overdue), multi-supplier sourcing, contingency planning | Mitigate | 2 | 2 | 2 | 1 | 6 | Leanne Mason | 2026-06-01 | Active | SAR refresh overdue — see APP_21
8 | R-08 | Culture / governance | Poor culture, communication failures, family-business governance gaps. | 2 | 1 | 3 | 3 | 12 | #TEAM philosophy, regular meetings, performance management, clear governance, ISO implementation | Mitigate | 1 | 1 | 2 | 2 | 6 | Aaron Mason | 2027-06-01 | Active
9 | R-09 | Legal & regulatory — water sector | Changes in legislation (Water (Special Measures) Act 2025, WIRS standards, water-quality regs, CDM updates, staff competency gaps). | 3 | 4 | 3 | 2 | 13 | APP_10 Legal Register (Rev 3), compliance audits, SOP 3.3, Management Review | Mitigate | 2 | 4 | 2 | 1 | 8 | Sean Ashton | 2026-10-01 | Active | Quarterly horizon-scan in place
10 | R-10 | Legal — Water (Special Measures) Act 2025 | Tighter client-pass-through clauses: spill-reporting, audit documentation, environmental-incident liability. Client water-cos under pressure will pass risk down. | 3 | 3 | 3 | 2 | 12 | Monitor new contract wording; legal review on any new framework | Mitigate + Transfer | 2 | 3 | 2 | 1 | 7 | Aaron Mason | 2026-06-01 | NEW | On each new contract award
11 | R-11 | Legal — Employment Rights Act 2025 | Day-one unfair-dismissal rights, zero-hours contract changes, Fair Work Agency, sick-pay reform. Phased commencement 2026-27. | 3 | 3 | 2 | 2 | 10 | Contracts and HR procedures review scheduled Q4 2026; Acas updates tracked | Mitigate | 2 | 3 | 1 | 1 | 6 | Leanne Mason | 2026-10-01 | NEW
12 | R-12 | Compliance — Worker Protection Act 2023 | New employer duty to prevent sexual harassment, in force 26 Oct 2024. Risk of 25% tribunal uplift for breach. | 3 | 4 | 2 | 2 | 11 | Sexual-harassment risk assessment (in progress), updated policy, training records | Mitigate | 2 | 4 | 1 | 1 | 7 | Leanne Mason | 2026-09-01 | NEW
13 | R-13 | Compliance — ISO standards transition | ISO 14001:2026 (published April 2026), ISO 9001:2026 (Q4 2026), ISO 45001:2027 — three simultaneous 3-year transitions by ~2029. | 3 | 3 | 4 | 3 | 18 | Transition plan to be drafted Q3 2026 (14001 first); aligned to recertification cycle Nov 2027 | Mitigate | 2 | 3 | 2 | 2 | 9 | Sean Ashton | 2026-09-01 | NEW
14 | R-14 | Operational — NUAR migration | Statutory National Underground Asset Register replacing LSBUD (DUAA 2025). Impact on CAT-scan procedure, operative training, commercial search workflow. | 2 | 3 | 3 | 3 | 14 | Watching brief on DESNZ commencement; CAT-scan SOP refresh planned | Mitigate | 2 | 3 | 2 | 2 | 9 | Jason May | 2026-09-01 | NEW | Review Q3 2026
15 | R-15 | Transport | Driving on company business. RTAs. Driver fatigue. Vehicle breakdowns. Public-liability incidents. | 3 | 3 | 3 | 3 | 15 | Fleet maintenance, driver training, daily checks, journey management, drivers' handbook, O-Licence compliance | Mitigate | 2 | 3 | 2 | 2 | 9 | Aaron Mason | 2027-06-01 | Active
16 | R-16 | Technology — AI | AI tools — accuracy, data-security, copyright, hallucinations, skills gap, implementation costs. | 2 | 2 | 3 | 2 | 10 | AI policy (draft), controlled pilot use for documentation, security measures, DUAA 2025 monitoring | Mitigate | 1 | 2 | 2 | 1 | 5 | Sean Ashton | 2026-12-01 | Active
17 | R-17 | Environmental — operational | Pollution incidents, waste breaches, protected species, spillages, non-containment of chlorinated water. | 3 | 4 | 2 | 2 | 11 | Environmental procedures, spill kits in van packs, waste-management SOPs, field training, incident response | Mitigate | 2 | 4 | 1 | 1 | 7 | Sean Ashton | 2027-06-01 | Active
18 | R-18 | Environmental — PFAS | Emerging UK REACH restrictions on per- and polyfluoroalkyl substances. Potential supply-chain disruption if current consumables are affected. | 2 | 2 | 2 | 2 | 8 | Monitor supplier SDSs for PFAS content; no current known use | Accept (monitor) | 1 | 2 | 1 | 1 | 4 | Sean Ashton | 2026-12-01 | NEW
19 | R-19 | Financial | Financial sustainability. Payment delays. Interest-rate / inflation. Economic downturn. Cash-flow issues. | 3 | 2 | 3 | 2 | 11 | Cash reserves, credit control, client diversity, cost monitoring, banking relationships | Mitigate | 2 | 2 | 2 | 1 | 6 | Leanne Mason | 2027-06-01 | Active
20 | R-20 | Climate | Climate change / extreme weather. Site flooding. Heat stress. Ground conditions. Working-day losses. 2025 was driest Feb-April since 1956. | 2 | 1 | 3 | 3 | 12 | Weather monitoring, flexible working, PPE, pumping equipment, emergency procedures, fleet fuel-demand planning | Mitigate | 2 | 1 | 2 | 2 | 7 | Jason May | 2027-06-01 | Active
21 | R-21 | Skills shortage — water sector | UK water industry faces documented shortage in digital / engineering / environmental roles during PR24 period. Competition for WIRS-certified operatives increasing. | 3 | 1 | 3 | 2 | 10 | Apprenticeship route, CPD budget, retention via #TEAM culture, cross-training to broaden ticket portfolio | Mitigate | 2 | 1 | 2 | 1 | 5 | Aaron Mason | 2026-09-01 | NEW

## Opportunities
A M Water Services — Opportunity Register
# | Ref | Category | Opportunity | Benefit | Owner | Target | Status | Notes
1 | O-01 | Recruitment | Local schools / universities / apprenticeships | Lower-cost talent pipeline; fresh perspectives | Aaron Mason | 2026-09-01 | Active
2 | O-02 | Digital / IT | Complete digital IMS rollout (this project) + transition to ISO27001-aligned information-security management | Reduces cyber risk R-02; supports client procurement | Sean Ashton | 2026-12-01 | In progress | IMS + Van Packs migration underway
3 | O-03 | Compliance | First-mover advantage in ISO 14001:2026 transition — publish case study | Marketing + audit evidence | Sean Ashton | 2027-06-01 | Active
4 | O-04 | Environmental | Electric-vehicle transition for fleet; cut fuel exposure (incl. benzene R-06); net-zero positioning | Cost reduction + reputational | Aaron Mason | 2027-12-01 | Active
5 | O-05 | Services | Resilience-services offer (emergency response, drought / burst-main callouts) — capitalising on 2025 drought + PR24 £500m net-zero funding | Revenue diversification | Aaron Mason | 2027-06-01 | Active
6 | O-06 | Services | Strategic partnerships / framework agreements with 1-2 Tier-1 water clients | Revenue predictability | Leanne Mason | 2026-09-01 | Active
7 | O-07 | Operations | NUAR early-adopter — become visible operator to water clients | Contract differentiator | Jason May | 2026-09-01 | NEW
8 | O-08 | Culture | Formal health-and-wellbeing programme linked to expanded health surveillance | Lower claims, better retention | Leanne Mason | 2026-12-01 | Active
9 | O-09 | Compliance | Consultancy side — Sean's offer extended to other small water-sector firms needing ISO / COSHH support | Ancillary revenue; sharpens own practice | Sean Ashton | 2027-06-01 | Active