## Summary
B2 Evidence Pack — Summary
As at 24 April 2026
By status
Status | Count | %
Ready | 63 | 64.95%
Partial | 17 | 17.53%
Gap | 9 | 9.278%
N/A | 8 | 8.247%
By category
Category | Items | Ready | Partial/Gap
Systems Assurance & Compliance | 9 | 6 | 3
Quality Control & Assurance | 13 | 9 | 4
Business Continuity | 2 | 1 | 1
Employment Practice & Human Rights | 5 | 4 | 1
Training & Capability / Competence Assessment | 5 | 3 | 2
Working Hours | 3 | 1 | 2
Workplace Safety | 22 | 15 | 7
Occupational Health | 7 | 4 | 3
Site Security | 2 | 0 | 2
Environmental Management | 11 | 10 | 1
Carbon Management | 3 | 0 | 3
Selection & Management of Sub-contractors | 5 | 4 | 1
Sourcing of Goods & Products | 4 | 2 | 2
Use of Work Equipment, Vehicles & Machines | 6 | 4 | 2

## B2 Evidence Log
A M Water Services — Achilles UVDB B2 Evidence Pack
As at 24 April 2026 · Audit expected June 2026 · Leanne Mason (director) / Sean Ashton (HSQE support)
Qn | B2 category | Evidence item | IMS document / note | Status | Action (if gap) | Owner | Target | Notes
1.1.1 | Systems Assurance & Compliance | ISO 9001:2015 certificate | ISO 9001 Certificate | Ready |  | Aaron Mason
1.1.1 | Systems Assurance & Compliance | ISO 14001:2015 certificate | ISO 14001 Certificate | Ready |  | Aaron Mason
1.1.1 | Systems Assurance & Compliance | ISO 45001:2018 certificate | ISO 45001 Certificate | Ready |  | Aaron Mason
1.1.2 | Systems Assurance & Compliance | CDM Policy / Procedures | APP_10 L2 CDM 2015 + policy framework in POL_HSQE series | Ready |  | Sean Ashton
1.1.2 | Systems Assurance & Compliance | Construction Phase Plan (if used) | Site-specific CPP produced per contract; generic template held | Partial | Produce CPP template / example and file as evidence | Jason May | 15/05/2026
1.1.3 | Systems Assurance & Compliance | Waste Carrier Licence | Waste Carrier Registration | Ready |  | Aaron Mason
1.1.4 | Systems Assurance & Compliance | Goods Vehicle Operator's Licence | Goods Vehicle Operator's Licence | Ready |  | Aaron Mason
1.1.4 | Systems Assurance & Compliance | FORS membership | Not currently held — AMWS is evaluating DVSA Earned Recognition instead (APP_10 L52a) | N/A | Disclose to auditor; reference monitoring status | Aaron Mason
1.1.5 | Systems Assurance & Compliance | Logistics RA / Fleet tracking | Fleet telematics in place; RA covers driving (RA_HO_12 Driving for Work) | Partial | Document fleet-management / tracking system formally as evidence page | Aaron Mason | 31/05/2026
1.2.1 | Quality Control & Assurance | Quality policy statement | POL_HSQE_20 — Quality Policy Statement | Ready |  | Aaron Mason
1.2.1 | Quality Control & Assurance | Quality responsibilities document | MAN_01a — Roles & Responsibilities | Ready |  | Aaron Mason
1.2.1 | Quality Control & Assurance | Quality Management System | MAN_01 — IMS Manual (scope includes QMS under ISO 9001) | Ready |  | Aaron Mason
1.2.2 | Quality Control & Assurance | Document control procedure | SOP 4.6 — Document Control + SOP 4.7 — Control of Records | Ready |  | Sean Ashton
1.2.2 | Quality Control & Assurance | Quality plan (if used) | Not used as a standalone QP — quality requirements are embedded in MS / SOPs / contract-specific RAMS | N/A | Disclose — explain QMS delivered via IMS process framework, not separate QP | Sean Ashton
1.2.2 | Quality Control & Assurance | Inspection & Test Plan (if used) | Not used formally — inspections are per MS / van checks | N/A | Disclose — consider producing a generic ITP template for 1.2 hour investment | Jason May | 31/05/2026
1.2.2 | Quality Control & Assurance | Snagging inspection record | QA_FM_07.0 Hygiene Audit + QA_FM_07.1 Van / Site Water-Quality Audit + client handover records | Ready | Collect recent 3-6 examples | Jason May | 15/05/2026
1.2.3 | Quality Control & Assurance | ISO 27001 certificate (if held) | Not held — AMWS is small; IT security managed via policy + external IT support | N/A | Disclose; see IT security policy row below | Leanne Mason
1.2.3 | Quality Control & Assurance | IT Security Policy | **Gap** — AMWS does not currently have a standalone IT security policy. Close-to-audit priority. | Gap | Draft IT security policy aligned to ISO 27001 Annex A controls (5-8 hrs) | Sean Ashton | 31/05/2026
1.2.4 | Quality Control & Assurance | Internal audit schedule | APP_20 — Internal Audits Programme | Ready |  | Sean Ashton
1.2.4 | Quality Control & Assurance | Examples of internal / site audits | 16 × IA202501–16 audit reports | Ready | Have 2-3 strongest examples pre-selected (Context & Leadership, Operations, Env) | Sean Ashton
1.2.5 | Quality Control & Assurance | Non-conformance reports + NC log | APP_21 — NC Register + 23 × CAR-2025 | Ready |  | Sean Ashton
1.2.5 | Quality Control & Assurance | Evidence of assessment of audit NCs | Management Review minutes + KPIs (APP_11) + Improvement register (IAF-2025-001 etc.) | Ready | Pull Sept 2025 MRM minutes showing CAR review | Sean Ashton
1.3.1 | Business Continuity | Business continuity plan / procedures | APP_17 — Disaster Recovery & Business Continuity Plan | Ready |  | Leanne Mason
1.3.1 | Business Continuity | BCP test / review records | **Gap** — no formal desktop exercise or test held yet (plan item 7.6 is scheduled for September 2026) | Gap | Run a short desktop exercise with Aaron + Leanne before the audit; document the scenario, findings and any actions (2 hrs) | Sean Ashton | 31/05/2026
1.4.1 | Employment Practice & Human Rights | Anti-bribery and corruption policy | POL_HSQE_04 — Anti-Bribery & Corruption Policy | Ready |  | Aaron Mason
1.4.2 | Employment Practice & Human Rights | Training records | APP_12 — Training Matrix + individual staff training records | Ready | Three of four statutory certs expired — see Gap List. Fresh training certs for Jason & Leanne before audit if possible. | Leanne Mason | 31/05/2026
1.4.3 | Employment Practice & Human Rights | Right-to-work procedure | **Partial** — POL_HSQE_17 (Illegal Workers) covers the policy. A formal RTW-check procedure is not separately documented. | Partial | Draft a short RTW procedure (1-2 hrs) and hold as HR process record | Leanne Mason | 15/05/2026
1.4.4 | Employment Practice & Human Rights | Sample personnel files incl. RTW (redacted) | Held by Leanne; not on IMS site (confidentiality) | Ready | Pre-select 2 redacted samples to show auditor | Leanne Mason | before audit
1.4.5 | Employment Practice & Human Rights | Modern Slavery Act (2015) policy statement | POL_HSQE_03 — Anti-Slavery & Human Trafficking Policy | Ready |  | Aaron Mason
1.5.1 | Training & Capability / Competence Assessment | Signed new-starter / site induction records | Induction Process Procedure (IPP001) + acknowledgement sheet (Van Packs) | Partial | Ensure most-recent signed inductions are in file — sample size 3 minimum | Leanne Mason | 15/05/2026
1.5.1 | Training & Capability / Competence Assessment | Induction training checklist / content guide | IPP001 — Induction Process Procedure | Ready |  | Leanne Mason
1.5.2 | Training & Capability / Competence Assessment | Job descriptions / competency matrix | JD001–004 + APP_12 Training Matrix + APP_13 Tickets & Qualifications | Ready |  | Leanne Mason
1.5.3 | Training & Capability / Competence Assessment | Training matrix / monitoring system | APP_12 — Training Matrix | Ready |  | Sean Ashton
1.5.3 | Training & Capability / Competence Assessment | Sample training records / certificates / licences | Staff Training Records + statutory certificate PDFs | Partial | Three statutory certs expired (Fire Marshal x2, First Aid x1). See Gap List; book replacement courses. | Leanne Mason | 31/05/2026
1.6.1 | Working Hours | Time sheets | HR_FM_09 Timesheet + HR_FM_12 Lorry & Support Staff Timesheet + QA_FM_09 Monthly Van Check | Ready | Sample 3 months of completed sheets | Leanne Mason
1.6.1 | Working Hours | Fatigue risk assessment | **Gap** — fatigue RA not currently documented as a standalone assessment. | Gap | Add a fatigue RA to the Home/Office RA set (RA_HO) — 2 hrs | Sean Ashton | 15/05/2026
1.6.1 | Working Hours | Opt-out agreement forms | Working Time Regulations 1998 opt-outs held by Leanne; template not on IMS | Partial | Upload blank opt-out template as a form (HR_FM_xx) | Leanne Mason | 15/05/2026
1.7.1 | Workplace Safety | Competent H&S support (internal or external) | Sean Ashton (HSQE Consultant, Onyx Operations) — external competent person — NEBOSH certificate on file | Ready |  | Aaron Mason
1.7.2 | Workplace Safety | Register of legislation | APP_10 — Legal & Compliance Register (Rev 3, April 2026 — 72 items) | Ready |  | Sean Ashton
1.7.2 | Workplace Safety | H&S policy statement | POL_HSQE_16 — Health & Safety Policy Statement | Ready |  | Aaron Mason
1.7.2 | Workplace Safety | H&S responsibilities document | MAN_01a — Roles & Responsibilities | Ready |  | Aaron Mason
1.7.3 | Workplace Safety | Senior management safety tours / audits | **Gap** — no formal scheduled safety-tour record by directors | Gap | Schedule a director site-tour per quarter; log each with date / site / observations (template in 1 hr) | Aaron Mason | 15/05/2026
1.7.4 | Workplace Safety | Risk assessment procedure | POL_HSQE_21 — Risk Assessment Policy + SOP 3.1 — Risk Identification | Ready |  | Sean Ashton
1.7.4 | Workplace Safety | Design risk assessment | AMWS does not undertake design — ISO 9001:2015 Clause 8.3 formally excluded (see MAN_01 Section 2.2) | N/A | Cite the exclusion to the auditor | Sean Ashton
1.7.5 | Workplace Safety | Site-specific RA & method statement | Van Packs — 22 field RAs (RA01–25) + 32 method statements (MS Section 2 + 3) | Ready |  | Jason May
1.7.5 | Workplace Safety | Generic RA & method statement | Van Packs — Section 2 generic MSs + Home/Office RAs (RA_HO_01–17) | Ready |  | Sean Ashton
1.7.6 | Workplace Safety | Permit to Work documentation | **Partial** — permits referenced in MS 3.3 Excavation (permit to dig) but no generic PTW template | Partial | Produce a generic PTW template (excavation / hot work / confined space) — 2 hrs | Sean Ashton | 31/05/2026
1.7.6 | Workplace Safety | RAMS briefing records | Acknowledgement Sheet (Van Packs) + site briefings | Ready | Sample 3 most-recent briefing records | Jason May
1.7.6 | Workplace Safety | Safety communication (toolbox talks) | **Gap** — no standing toolbox-talk schedule or records found | Gap | Introduce monthly TBT programme; first three TBTs pre-audit; template + log (3 hrs) | Jason May | 31/05/2026
1.7.7 | Workplace Safety | PPE procedure | POL_HSQE_19 — PPE Policy + SOP 8.4 — PPE | Ready |  | Sean Ashton
1.7.7 | Workplace Safety | Signed PPE register / record | HS_FM_11 PPE Request Form — issue records per individual | Partial | Consolidate into a signed PPE issue register (Excel) — 1 hr | Leanne Mason | 15/05/2026
1.7.8 | Workplace Safety | COSHH procedure | SOP 8.5 — COSHH + POL_HSQE_08 | Ready |  | Sean Ashton
1.7.8 | Workplace Safety | COSHH assessments | 24 × COSHH assessments (Rev 2, April 2026) | Ready |  | Sean Ashton
1.7.8 | Workplace Safety | Spill kits / bunding / COSHH control | Van-pack spill kits + bunded fuel storage | Ready | Physical evidence for site-audit element | Jason May
1.7.9 | Workplace Safety | First aid procedure, RA, certificates | POL_HSQE_14 — First Aid + SOP 8.3 + RA_HO_16 + RA20 First Aid Needs (Van Packs) | Partial | Leanne's Emergency First Aid cert expired 30/10/25 — rebook | Leanne Mason | 31/05/2026
1.7.9 | Workplace Safety | Fire / emergency arrangements + drill records | APP_16 — Emergency Prep & Response Matrix + APP_18 — Emergency Equipment Log + SOP 8.15 Fire | Partial | Plan item 7.5 schedules fire-drill Oct; bring forward to pre-audit | Jason May | 31/05/2026
1.7.10 | Workplace Safety | Accident / incident / near-miss reporting | SOP 8.1 — Accident, Incident & Near-Miss + POL_HSQE_01 Accident Investigation + Incidents section | Ready |  | Sean Ashton
1.7.10 | Workplace Safety | Enforcement notices in last 5 years | None received in the period — to be confirmed by director statement | Ready | Written statement from Aaron pre-audit | Aaron Mason | before audit
1.7.10 | Workplace Safety | Accident statistics — last 4 years | APP_22 — Accident Statistics Register | Ready | Confirm register covers full 4-year window | Sean Ashton
1.8.1 | Occupational Health | OH responsibilities (internal or external) | MAN_01a Roles & Responsibilities — Sean Ashton / Aaron Mason share OH oversight | Ready |  | Aaron Mason
1.8.1 | Occupational Health | Occupational health procedure | SOP 8.7 — Health Surveillance | Ready | Update SOP 8.7 to explicitly cover benzene (EH70) from COSHH_23 | Sean Ashton | 15/05/2026
1.8.1 | Occupational Health | OH screening / monitoring records | HAVS monitoring, benzene surveillance (now triggered) | Partial | Activate 6-monthly benzene surveillance (per APP_05 R-06); at least baseline record before audit | Sean Ashton | 31/05/2026
1.8.1 | Occupational Health | Alcohol & drug policy | POL_HSQE_02 — Alcohol & Drugs Policy | Ready |  | Aaron Mason
1.8.1 | Occupational Health | Employee Assistance Programme (EAP) | **Gap** — no EAP in place | Gap | Decision needed: enrol in a low-cost EAP (e.g. Health Assured, Vitality, or local provider) OR disclose absence with documented rationale | Aaron Mason | 15/05/2026
1.8.1 | Occupational Health | Mental Health First Aid certificates | Jason May (EXP 07/11/2026) + Leanne Mason (EXP 13/11/2026) — on file | Ready |  | Leanne Mason
1.8.1 | Occupational Health | Mental Health policy | **Gap** — not currently a standalone policy (touched on in POL_HSQE_26 Welfare) | Gap | Draft a short Mental Health & Wellbeing policy (2 hrs) — referencing existing MHFA cover and EAP decision | Sean Ashton | 31/05/2026
1.9.1 | Site Security | Security arrangements (CCTV / guards etc.) | AMWS site work is temporary / public-highway based; no fixed-site security; typical arrangements are site-specific fencing + client arrangements on live-main work | N/A | Document the approach as a short paragraph so the auditor sees it's a considered position | Jason May | 15/05/2026
1.9.1 | Site Security | SIA licences | N/A — no security personnel employed by AMWS | N/A | Confirm to auditor | Aaron Mason
1.10.1 | Environmental Management | Environmental policy statement | POL_HSQE_10 — Environmental Policy | Ready |  | Aaron Mason
1.10.1 | Environmental Management | EMS / manual | MAN_01 — IMS Manual (ISO 14001 scope) | Ready |  | Aaron Mason
1.10.1 | Environmental Management | Qualified environmental support | Sean Ashton — NEBOSH-certified HSQE; external competent support | Ready |  | Aaron Mason
1.10.2 | Environmental Management | Legislation register | APP_10 — Legal & Compliance Register (72 items incl. 8 environmental L26–L32a) | Ready |  | Sean Ashton
1.10.2 | Environmental Management | Aspects & impacts register | APP_06 — Aspect Identification Log | Ready |  | Sean Ashton
1.10.3 | Environmental Management | Environmental audit / inspection records | IA202507 — Environmental Management internal audit | Ready |  | Sean Ashton
1.10.4 | Environmental Management | Waste management procedure / policy | SOP 9.4 — Management of Waste + SOP 9.5 — Hazardous Waste | Ready |  | Sean Ashton
1.10.4 | Environmental Management | Recycling initiatives | Skip-hire with segregation; scrap metal diverted from landfill; electronic waste via approved recycler | Partial | Document current initiatives as a short page (1 hr) | Aaron Mason | 15/05/2026
1.10.4 | Environmental Management | Waste Carrier Licence | Waste Carrier Registration Certificate (valid to 12/08/2028) | Ready |  | Aaron Mason
1.10.4 | Environmental Management | Waste Transfer Notes | Retained by Leanne per transaction; 3-year retention per duty-of-care | Ready | Sample 3-5 recent WTNs to have ready | Leanne Mason | before audit
1.10.5 | Environmental Management | Spill response arrangements / equipment | Van-pack spill kits + spill-response reference in COSHH assessments (Section 8) + SOP 5.4 Emergency Preparedness | Ready |  | Jason May
1.11.1 | Carbon Management | Carbon footprint recording | **Gap** — no formal carbon-footprint record currently produced | Gap | Produce a Scope 1 / 2 carbon statement using fuel records + electricity bills for 2025 (4-6 hrs). Even a first-cut baseline satisfies the 'evidence of recording' test. | Sean Ashton | 31/05/2026
1.11.1 | Carbon Management | Sustainability / CSR report | POL_HSQE_07 — Corporate Social Responsibility covers the CSR statement; no annual report produced | Partial | Draft a 1-page annual sustainability note for 2025 covering waste segregation, fleet efficiency, community engagement (1-2 hrs) | Aaron Mason | 31/05/2026
1.11.1 | Carbon Management | Sustainability objectives and targets | APP_11 — HSQE Objectives & KPIs Register includes environmental KPIs | Partial | Elevate 2-3 environmental KPIs to explicit 'sustainability objectives' with named targets (30 min) | Sean Ashton | 15/05/2026
1.12.1 | Selection & Management of Sub-contractors | JD / details of person responsible for supplier selection | MAN_01a Roles & Responsibilities — Leanne Mason leads supplier / subcontractor selection | Ready |  | Leanne Mason
1.12.1 | Selection & Management of Sub-contractors | Pre-qualification / subcontractor procedure | SOP 5.3 — Supplier Evaluation & Approval | Ready |  | Sean Ashton
1.12.1 | Selection & Management of Sub-contractors | Pre-qualification questionnaire (PQQ) | 32 × Supplier PQQs (one per approved supplier) | Ready |  | Leanne Mason
1.12.2 | Selection & Management of Sub-contractors | Approved suppliers list | APP_19 — Approved Supplier List | Ready |  | Leanne Mason
1.12.2 | Selection & Management of Sub-contractors | Supplier / subcontractor monitoring | 32 × Supplier Annual Reviews (SARs) per supplier — **OVERDUE** (Sept 2025) | Gap | **BLOCKING** — All 32 SARs must be refreshed before the Achilles audit. Bulk email template + chase. Est. 1 hr per supplier. 32 hrs. | Leanne Mason | 31/05/2026
1.13.1 | Sourcing of Goods & Products | CFSI (Counterfeit, Fraudulent, Suspect Items) — nuclear only | N/A — AMWS does not work in nuclear sector | N/A | Confirm to auditor | Sean Ashton
1.13.2 | Sourcing of Goods & Products | Chain of custody (FSC timber etc.) | Limited timber use; any shoring boards sourced from established UK builders' merchants | Partial | Request FSC certificates from Jewson and any other timber suppliers for supplier file | Leanne Mason | 31/05/2026
1.13.3 | Sourcing of Goods & Products | Anti-bribery methods in supply chain | POL_HSQE_04 — Anti-Bribery & Corruption Policy — PQQ includes anti-bribery declaration | Ready |  | Leanne Mason
1.13.4 | Sourcing of Goods & Products | Modern slavery in supply chain | POL_HSQE_03 — Anti-Slavery & Human Trafficking Policy + PQQ declaration | Ready |  | Leanne Mason
1.14.1 | Use of Work Equipment, Vehicles & Machines | Calibration / PAT records | APP_14 — Calibration & Equipment Maintenance Log | Ready | Confirm PAT test records ≤12 months old | Jason May
1.14.1 | Use of Work Equipment, Vehicles & Machines | Maintenance plans for plant / equipment | APP_14 + HS_FM_26 PUWER Register | Ready |  | Jason May
1.14.1 | Use of Work Equipment, Vehicles & Machines | Inspector qualifications | LOLER-competent persons documented in APP_12 Training Matrix; external thorough-examiner contracted where required | Partial | Collate LOLER / statutory inspector evidence on one page | Jason May | 15/05/2026
1.14.1 | Use of Work Equipment, Vehicles & Machines | Thorough inspection records (LOLER etc.) | LOLER 6-monthly TE certificates on file per asset | Ready | Recent 3 TE certs ready to show | Jason May
1.14.1 | Use of Work Equipment, Vehicles & Machines | Hired-equipment suitability check | Pre-hire checks via supplier PQQ (HSE Jewson, GAP, Speedy etc.); on-delivery inspection per driver handbook | Partial | Document a hired-equipment check procedure / checklist (1 hr) | Jason May | 15/05/2026
1.14.1 | Use of Work Equipment, Vehicles & Machines | Pre-use / weekly inspection examples | QA_FM_08 Weekly Van Check + QA_FM_09 Monthly Van Check + daily plant checks | Ready | Sample 3-5 recent completed check sheets | Jason May