## Summary
B2 Gap Closure — Summary
As at 24 April 2026
Priority | Items | Closed | Est. hrs
P1 | 6 | 0 | 43
P2 | 9 | 0 | 18.5
P3 | 8 | 0 | 1
By owner
Aaron Mason | 7 |  | 5
Jason May | 2 |  | 3.5
Leanne Mason | 5 |  | 35
Sean Ashton | 9 |  | 19

## Gap Closure
AMWS — Achilles B2 Gap Closure Tracker
As at 24 April 2026 · Audit expected June 2026 · 23 items
# | Priority | Gap | B2 ref | Owner | Target | Est. hrs | Closure action | Status | Notes
1 | P1 | 32 Supplier Annual Reviews (SARs) all overdue (Sept 2025) | 1.12.2 | Leanne Mason | 31/05/2026 | 32 | Bulk email template; chase 32 suppliers; capture responses in SAR docs on IMS. Single biggest audit risk. | Not started
2 | P1 | BCP test / review records | 1.3.1 | Sean Ashton | 31/05/2026 | 2 | Short desktop exercise with Aaron + Leanne. Document scenario, response actions, issues identified, action register. | Not started
3 | P1 | Senior management safety tours / inspections | 1.7.3 | Aaron Mason | 15/05/2026 | 1 | One-page director site-tour template. One completed tour before audit; quarterly recurring thereafter. | Not started
4 | P1 | Toolbox talk programme + records | 1.7.6 | Jason May | 31/05/2026 | 3 | Monthly TBT schedule. 3 topics before audit (excavation, HAVS, benzene/fuels). Attendance records. | Not started
5 | P1 | Carbon footprint recording | 1.11.1 | Sean Ashton | 31/05/2026 | 5 | Scope 1 & 2 baseline statement from 2025 fuel + electricity bills. First-cut baseline with caveats sufficient. | Not started
6 | P1 | 3 expired statutory training certificates | 1.5.3 | Leanne Mason | 31/05/2026 | 0 | Book replacement courses — Jason FM, Leanne FM + EFAW. Check Aaron's Fire Marshal cert (not on file). | Not started
7 | P2 | IT Security Policy | 1.2.3 | Sean Ashton | 31/05/2026 | 6 | Standalone policy aligned to ISO 27001 Annex A — access control, data classification, backup/recovery, incident response, passwords, third-party IT. | Not started
8 | P2 | Right-to-Work procedure | 1.4.3 | Leanne Mason | 15/05/2026 | 1.5 | Short procedure: pre-employment checks, documents accepted, retention, share-code verification, refresh cycle. | Not started
9 | P2 | Permit to Work template (generic) | 1.7.6 | Sean Ashton | 31/05/2026 | 2 | Generic PTW template — excavation, hot work, confined space. Cross-reference MS 2.9, MS 2.24, MS 3.3. | Not started
10 | P2 | Signed PPE register | 1.7.7 | Leanne Mason | 15/05/2026 | 1 | Consolidate HS_FM_11 issue forms into a single signed Excel register per person per item. | Not started
11 | P2 | Fatigue Risk Assessment | 1.6.1 | Sean Ashton | 15/05/2026 | 2 | RA_HO_18 — drivers' hours, overnight sites, callouts, HAVS long-day interactions. | Not started
12 | P2 | Mental Health policy | 1.8.1 | Sean Ashton | 31/05/2026 | 2 | Short standalone policy referencing existing MHFA cover and EAP decision. Complements POL_HSQE_26 Welfare. | Not started
13 | P2 | Employee Assistance Programme (EAP) | 1.8.1 | Aaron Mason | 15/05/2026 | 1 | Commercial decision — enrol (Health Assured / Vitality — £5-£15 pp/mo) OR document rationale for not having one. | Not started
14 | P2 | Sustainability report + explicit targets | 1.11.1 | Aaron Mason | 31/05/2026 | 2 | 1-page 2025 sustainability note. Elevate 2-3 env KPIs from APP_11 as explicit objectives. | Not started
15 | P2 | Recycling initiatives write-up | 1.10.4 | Aaron Mason | 15/05/2026 | 1 | 1-page summary: skip segregation, scrap metal, e-waste, packaging, toner/battery recycling. | Not started
16 | P3 | FORS membership | 1.1.4 | Aaron Mason | — | 0 | Not held. Monitoring DVSA Earned Recognition (APP_10 L52a + APP_05 R-21). Disclose. | Not started
17 | P3 | Quality plan / ITP | 1.2.2 | Sean Ashton | — | 0 | Not used standalone — embedded in MS + RAMS. Disclose. Consider ITP template post-audit. | Not started
18 | P3 | ISO 27001 certification | 1.2.3 | Aaron Mason | — | 0 | Not held. IT security via new policy + external IT support. Forward look in APP_05 O-02. | Not started
19 | P3 | Design Risk Assessment | 1.7.4 | Sean Ashton | — | 0 | AMWS does not design. ISO 9001:2015 Clause 8.3 formally excluded (MAN_01 s2.2). Cite exclusion. | Not started
20 | P3 | CFSI (nuclear only) | 1.13.1 | Sean Ashton | — | 0 | AMWS does not work in nuclear sector. N/A. | Not started
21 | P3 | SIA security licences | 1.9.1 | Aaron Mason | — | 0 | No security personnel. N/A. | Not started
22 | P3 | Site security arrangements | 1.9.1 | Jason May | 15/05/2026 | 0.5 | Work is temporary / public-highway based; short paragraph documenting considered position. | Not started
23 | P3 | FSC certificates for timber | 1.13.2 | Leanne Mason | 31/05/2026 | 0.5 | Request FSC certs from Jewson and other timber suppliers for supplier file. | Not started